## Build Info
Rustic Playground — Test Plan v0.3.4
Version | 0.3.4
Edition | Rust Edition
Plan Date | 2026-04-07 (updated after Bug 2 found on VM)
macOS Minimum | 12 Monterey
Build Command | VITE_EDITION=rust cargo tauri build --config editions/rust.json
Dev Command | VITE_EDITION=rust cargo tauri dev --config editions/rust.json
Storage Path | ~/Library/Application Support/com.rustic-playground.rust/
Test Rounds
Round 1 | Full Tahoe test pass — all features, main regression matrix
Round 2 | v0.3.4 Toolchain Fix Wizard — 4 branches (healthy, missing components, no default, not installed)
Round 3 | Edition Isolation — Rust Edition alongside Power Edition
Round 4 | VM Smoke Test — macOS 12 / 13 / 14 / 15 (Parallels on Mac Studio)
Priority Legend
Critical | Must pass. Blocks release if failing.
High | Strong fail signal. Should pass; investigate + fix before ship.
Medium | Polish / important UX. Log as issue if failing.
Low | Cosmetic / nice-to-have. Track but unlikely to block.
VM Test Order | 12 Monterey → 13 Ventura → 14 Sonoma → 15 Sequoia
VM Notes | 12 Monterey is highest-risk (floor). If it fails, fall back to 13 Ventura as the minimum.
VANILLA RULE | MANDATORY: Every VM must be vanilla — no Xcode CLT, no rustup, no brew, no node, no python, no dev tools whatsoever.
Why vanilla | Dev machines accumulate invisible dependencies over years. Bug 2 (Rust cannot link without CLT) was MISSED on the dev MacBook because Xcode was installed first. It was only caught on a clean VM. Every first-launch regression test must start from a vanilla snapshot.
Precheck | Before each VM test run: verify xcode-select -p fails, which cargo returns nothing, which brew returns nothing, ~/.cargo does not exist. See Round 4 "Vanilla State Precheck" section.

## R1 — Main Tests (Tahoe)
Round 1: Full Feature Test Pass (macOS 26 Tahoe)
# | Section | Test | Priority | Pass? | Notes
EDITION IDENTITY & BRANDING
1 | EDITION IDENTITY & BRANDING | App launches without crash | Critical
2 | EDITION IDENTITY & BRANDING | Dock icon: new Rust Edition swing set icon (fn carved in wood) | Low
3 | EDITION IDENTITY & BRANDING | Dock icon: proper size — not touching activity dot | Low
4 | EDITION IDENTITY & BRANDING | Menu bar: shows 'Rustic Playground — The Rust Edition' | Medium
5 | EDITION IDENTITY & BRANDING | Window title: 'Rustic Playground — The Rust Edition' | Medium
6 | EDITION IDENTITY & BRANDING | About modal: shows 'Rustic Playground — The Rust Edition' | Medium
7 | EDITION IDENTITY & BRANDING | About modal: shows tagline 'A focused playground for learning Rust.' | Low
8 | EDITION IDENTITY & BRANDING | About modal: version matches tauri.conf.json (0.3.4) | High
WELCOME WIZARD (EDITION-AWARE)
9 | WELCOME WIZARD (EDITION-AWARE) | Wizard appears on first launch | Critical
10 | WELCOME WIZARD (EDITION-AWARE) | Wizard title: 'Welcome to Rustic Playground — The Rust Edition' | Medium
11 | WELCOME WIZARD (EDITION-AWARE) | Wizard steps: Toolchain → Appearance → The Rust Book → Finish (NO Languages step) | High
12 | WELCOME WIZARD (EDITION-AWARE) | Step 1 — Toolchain (singular, not 'Toolchains') | Low
13 | WELCOME WIZARD (EDITION-AWARE) | Toolchain step: shows only Rust toolchain status (cargo, rustc, rustfmt, clippy) | High
14 | WELCOME WIZARD (EDITION-AWARE) | Toolchain step: no Clang/Zig/Swift toolchain checks | Medium
15 | WELCOME WIZARD (EDITION-AWARE) | Toolchain step: green indicators for installed tools | High
16 | WELCOME WIZARD (EDITION-AWARE) | Toolchain step: re-check button works | High
17 | WELCOME WIZARD (EDITION-AWARE) | Step 2 — Appearance | Medium
18 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: theme dropdown shows System, Light, Dark, Rust only | Medium
19 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: NO Auto (match language) option | Low
20 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: NO Zig/Swift/Sea Green themes | Medium
21 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: theme optgroup label is 'Language' (singular, not 'Languages') | Low
22 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: font size/family/tab size controls work | Medium
23 | WELCOME WIZARD (EDITION-AWARE) | Appearance step: live preview updates | Medium
24 | WELCOME WIZARD (EDITION-AWARE) | Step 3 — The Rust Book (specific name, not generic 'Books') | Low
25 | WELCOME WIZARD (EDITION-AWARE) | Book step: checkbox to load The Rust Book examples | Medium
26 | WELCOME WIZARD (EDITION-AWARE) | Book step: no K&R C Book / Swift Book options | Medium
27 | WELCOME WIZARD (EDITION-AWARE) | Step 4 — Finish | Medium
28 | WELCOME WIZARD (EDITION-AWARE) | Finish summary: shows selected theme | Low
29 | WELCOME WIZARD (EDITION-AWARE) | Finish summary: shows Rust toolchain status | Medium
30 | WELCOME WIZARD (EDITION-AWARE) | Finish summary: shows book loading choice | Low
31 | WELCOME WIZARD (EDITION-AWARE) | Finish summary: no Languages row | Low
32 | WELCOME WIZARD (EDITION-AWARE) | Click Finish → wizard closes, main UI appears | Critical
33 | WELCOME WIZARD (EDITION-AWARE) | Wizard does NOT reappear on second launch | High
SETTINGS — Cmd+, (EDITION-AWARE)
34 | SETTINGS — Cmd+, (EDITION-AWARE) | Settings modal opens with Cmd+, | Critical
35 | SETTINGS — Cmd+, (EDITION-AWARE) | Settings tabs: Toolchain, Appearance, The Rust Book (NO Languages tab) | High
36 | SETTINGS — Cmd+, (EDITION-AWARE) | Toolchain tab label: 'Toolchain' (singular) | Low
37 | SETTINGS — Cmd+, (EDITION-AWARE) | Toolchain tab: only Rust tools shown | High
38 | SETTINGS — Cmd+, (EDITION-AWARE) | Appearance tab: theme dropdown — System, Light, Dark, Rust only | Medium
39 | SETTINGS — Cmd+, (EDITION-AWARE) | Appearance tab: no Auto theme, no Zig/Swift/Sea Green | Medium
40 | SETTINGS — Cmd+, (EDITION-AWARE) | Appearance tab: optgroup 'Language' (singular) | Low
41 | SETTINGS — Cmd+, (EDITION-AWARE) | Book tab: labeled 'The Rust Book' (specific name) | Low
42 | SETTINGS — Cmd+, (EDITION-AWARE) | Book tab: Rust Book load/remove only, no other books | Medium
43 | SETTINGS — Cmd+, (EDITION-AWARE) | Font size / family / tab size changes apply | Medium
44 | SETTINGS — Cmd+, (EDITION-AWARE) | Reset Defaults works | Medium
45 | SETTINGS — Cmd+, (EDITION-AWARE) | Save persists, Cancel discards | High
PROJECT SWITCHER (EDITION-AWARE)
46 | PROJECT SWITCHER (EDITION-AWARE) | No language badge on active project pill | Low
47 | PROJECT SWITCHER (EDITION-AWARE) | No language badge on project list items | Low
48 | PROJECT SWITCHER (EDITION-AWARE) | New project: no type toggle (Rust only, auto-selected) | Medium
49 | PROJECT SWITCHER (EDITION-AWARE) | New project: creates Rust project without asking for type | Medium
50 | PROJECT SWITCHER (EDITION-AWARE) | Project dropdown: user projects at top, books at bottom | Medium
51 | PROJECT SWITCHER (EDITION-AWARE) | Search filter works | Medium
52 | PROJECT SWITCHER (EDITION-AWARE) | Duplicate / Rename / Delete project — all work | High
53 | PROJECT SWITCHER (EDITION-AWARE) | Book projects: rename/delete hidden | Medium
RUST — PROJECT & PLAYGROUND CRUD
54 | RUST — PROJECT & PLAYGROUND CRUD | Create new Rust project | Critical
55 | RUST — PROJECT & PLAYGROUND CRUD | Create new playground (Cmd+N) | Critical
56 | RUST — PROJECT & PLAYGROUND CRUD | Playground appears in sidebar + tab bar | High
57 | RUST — PROJECT & PLAYGROUND CRUD | Default fn main() code in editor | High
58 | RUST — PROJECT & PLAYGROUND CRUD | Rename playground | High
59 | RUST — PROJECT & PLAYGROUND CRUD | Duplicate playground | High
60 | RUST — PROJECT & PLAYGROUND CRUD | Delete playground | High
61 | RUST — PROJECT & PLAYGROUND CRUD | Switch between multiple playgrounds via tabs | High
62 | RUST — PROJECT & PLAYGROUND CRUD | Template: Hello World | Medium
63 | RUST — PROJECT & PLAYGROUND CRUD | Template: CLI Args | Medium
64 | RUST — PROJECT & PLAYGROUND CRUD | Template: File I/O | Medium
65 | RUST — PROJECT & PLAYGROUND CRUD | Template: JSON Parsing (auto-adds serde_json) | Medium
66 | RUST — PROJECT & PLAYGROUND CRUD | Template: HTTP Request | Medium
67 | RUST — PROJECT & PLAYGROUND CRUD | Template: Multithreading | Medium
68 | RUST — PROJECT & PLAYGROUND CRUD | Template: Error Handling | Medium
69 | RUST — PROJECT & PLAYGROUND CRUD | Template: Struct & Impl | Medium
70 | RUST — PROJECT & PLAYGROUND CRUD | Template: Enum & Match | Medium
71 | RUST — PROJECT & PLAYGROUND CRUD | Template: Iterator Chains | Medium
72 | RUST — PROJECT & PLAYGROUND CRUD | Template: Unit Tests | Medium
73 | RUST — PROJECT & PLAYGROUND CRUD | Rename project | High
74 | RUST — PROJECT & PLAYGROUND CRUD | Delete project | High
75 | RUST — PROJECT & PLAYGROUND CRUD | Duplicate project | High
RUST — EDITOR, RUN & LIVE CHECKING
76 | RUST — EDITOR, RUN & LIVE CHECKING | Syntax highlighting for Rust | Medium
77 | RUST — EDITOR, RUN & LIVE CHECKING | Line numbers visible | Low
78 | RUST — EDITOR, RUN & LIVE CHECKING | Bracket matching | Low
79 | RUST — EDITOR, RUN & LIVE CHECKING | Auto-indent on Enter | Low
80 | RUST — EDITOR, RUN & LIVE CHECKING | Cmd+Z undo / Cmd+Shift+Z redo | High
81 | RUST — EDITOR, RUN & LIVE CHECKING | Cmd+F find / Cmd+H replace | Medium
82 | RUST — EDITOR, RUN & LIVE CHECKING | Cmd+/ toggle comment | Medium
83 | RUST — EDITOR, RUN & LIVE CHECKING | Tab indent / Shift+Tab dedent | Low
84 | RUST — EDITOR, RUN & LIVE CHECKING | Font size matches Settings | Medium
85 | RUST — EDITOR, RUN & LIVE CHECKING | Font family matches Settings | Medium
86 | RUST — EDITOR, RUN & LIVE CHECKING | Tab size matches Settings | Medium
87 | RUST — EDITOR, RUN & LIVE CHECKING | Run (Cmd+R) — cargo run executes | Critical
88 | RUST — EDITOR, RUN & LIVE CHECKING | Output streams live (line by line) | Critical
89 | RUST — EDITOR, RUN & LIVE CHECKING | Stdout displays correctly | Critical
90 | RUST — EDITOR, RUN & LIVE CHECKING | Stderr in red (theme-aware) | High
91 | RUST — EDITOR, RUN & LIVE CHECKING | Compilation error shows in output | High
92 | RUST — EDITOR, RUN & LIVE CHECKING | Panic message shows in output | High
93 | RUST — EDITOR, RUN & LIVE CHECKING | Stop button kills process | High
94 | RUST — EDITOR, RUN & LIVE CHECKING | Stop-and-run confirmation dialog | High
95 | RUST — EDITOR, RUN & LIVE CHECKING | stdin input field appears for read_line() | Medium
96 | RUST — EDITOR, RUN & LIVE CHECKING | stdin appears on cargo 'Running' detection | Medium
97 | RUST — EDITOR, RUN & LIVE CHECKING | Live check: typo → red squiggle (~300ms) | High
98 | RUST — EDITOR, RUN & LIVE CHECKING | Live check: fix typo → squiggle clears | High
99 | RUST — EDITOR, RUN & LIVE CHECKING | Live check: multiple errors shown | Medium
100 | RUST — EDITOR, RUN & LIVE CHECKING | Copy Code (Cmd+Shift+C) | Medium
101 | RUST — EDITOR, RUN & LIVE CHECKING | Console copy button | Medium
102 | RUST — EDITOR, RUN & LIVE CHECKING | Console ANSI colors | Medium
103 | RUST — EDITOR, RUN & LIVE CHECKING | Console timestamps | Low
RUST — EXPORT
104 | RUST — EXPORT | Export project (Cmd+Shift+E) | High
105 | RUST — EXPORT | Export creates standalone CLI playground + README | High
106 | RUST — EXPORT | Exported project compiles with cargo run | High
RUST — DEPENDENCY MANAGER
107 | RUST — DEPENDENCY MANAGER | Add crate via toolbar | High
108 | RUST — DEPENDENCY MANAGER | Crate appears in Cargo.toml | High
109 | RUST — DEPENDENCY MANAGER | Remove crate | High
110 | RUST — DEPENDENCY MANAGER | Crate removed from Cargo.toml | High
111 | RUST — DEPENDENCY MANAGER | Run with added dependency compiles | High
RUST BOOK — LOAD, READ-ONLY, REMOVE
112 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Learn menu → The Rust Book → Load Examples | High
113 | RUST BOOK — LOAD, READ-ONLY, REMOVE | 20 chapter projects created | High
114 | RUST BOOK — LOAD, READ-ONLY, REMOVE | First chapter auto-opens | Medium
115 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Toast shows count | Low
116 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Each chapter has attribution.md | Medium
117 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: editor read-only | High
118 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Read-only pill in toolbar | Medium
119 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: book + lock icons in sidebar | Medium
120 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Save disabled | High
121 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Rename/Delete hidden in context menu | Medium
122 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Cmd+N does nothing | Medium
123 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Cut/Paste disabled in Edit menu | Medium
124 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Copy Code still works | Medium
125 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: lock toggle disabled | Medium
126 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Book project: Export still works | Medium
127 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Load again → 'already loaded' toast | Medium
128 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Learn → Remove → all book projects gone | Medium
129 | RUST BOOK — LOAD, READ-ONLY, REMOVE | Re-load after remove — fresh chapters | Medium
130 | RUST BOOK — LOAD, READ-ONLY, REMOVE | All 20 chapters compile without warnings | High
COPY TO PROJECT
131 | COPY TO PROJECT | Right-click book playground → 'Copy to Project…' | Medium
132 | COPY TO PROJECT | Modal shows target project dropdown (user Rust projects only) | Medium
133 | COPY TO PROJECT | Enter name, confirm → playground created in target | Medium
134 | COPY TO PROJECT | Switch to target → copied playground is editable | Medium
PER-PLAYGROUND LOCKING
135 | PER-PLAYGROUND LOCKING | Lock toggle visible in toolbar (user project) | High
136 | PER-PLAYGROUND LOCKING | Click lock → red lock, editor read-only | High
137 | PER-PLAYGROUND LOCKING | Click unlock → green unlock, editor editable | High
138 | PER-PLAYGROUND LOCKING | Locked: Save disabled | High
139 | PER-PLAYGROUND LOCKING | Lock icon in sidebar | Medium
140 | PER-PLAYGROUND LOCKING | Lock state persists across tab switches | High
141 | PER-PLAYGROUND LOCKING | Lock state persists after quit + relaunch | High
142 | PER-PLAYGROUND LOCKING | Book projects: lock toggle disabled | Medium
143 | PER-PLAYGROUND LOCKING | Lock colors correct in all Rust Edition themes | Low
144 | PER-PLAYGROUND LOCKING | Lock dirty playground then press ⌘S → file saves (lock only prevents editing) | Medium
145 | PER-PLAYGROUND LOCKING | Lock clean playground then press ⌘S → Save button disabled (nothing to save) | Medium
146 | PER-PLAYGROUND LOCKING | Book project save button → disabled (book always read-only) | Medium
147 | PER-PLAYGROUND LOCKING | Lock playground then run (⌘R) → file saves and compiles normally | Medium
148 | PER-PLAYGROUND LOCKING | Lock playground A then switch to playground B → B is unlocked, editor editable | High
149 | PER-PLAYGROUND LOCKING | Lock playground A → sidebar shows lock icon only on A | Medium
150 | PER-PLAYGROUND LOCKING | Lock A then lock B → both have independent lock icons in sidebar | Medium
151 | PER-PLAYGROUND LOCKING | Unlock A while B stays locked → A icon removed, B remains | High
THEMES (RUST EDITION — 4 THEMES)
152 | THEMES (RUST EDITION — 4 THEMES) | Theme: System — matches macOS appearance | High
153 | THEMES (RUST EDITION — 4 THEMES) | Theme: Light — light bg, dark text | High
154 | THEMES (RUST EDITION — 4 THEMES) | Theme: Dark — dark bg, light text | High
155 | THEMES (RUST EDITION — 4 THEMES) | Theme: Rust — earthy palette, espresso bg, Rust-red accents | High
156 | THEMES (RUST EDITION — 4 THEMES) | No Auto / Zig / Swift / Sea Green themes available anywhere | Medium
157 | THEMES (RUST EDITION — 4 THEMES) | Live preview in Settings | Medium
158 | THEMES (RUST EDITION — 4 THEMES) | Cancel → theme reverts | Medium
159 | THEMES (RUST EDITION — 4 THEMES) | Save → theme persists after relaunch | High
160 | THEMES (RUST EDITION — 4 THEMES) | Monaco editor matches app theme in all 4 | Medium
161 | THEMES (RUST EDITION — 4 THEMES) | Sidebar, toolbar, output themed consistently | Medium
162 | THEMES (RUST EDITION — 4 THEMES) | Stderr red readable in Light (#d42020) | Medium
163 | THEMES (RUST EDITION — 4 THEMES) | Stderr red readable in all themes | Medium
HELP MODAL (EDITION-AWARE)
164 | HELP MODAL (EDITION-AWARE) | Cmd+Shift+/ opens Help modal | High
165 | HELP MODAL (EDITION-AWARE) | Title: 'Rustic Playground — The Rust Edition' | Low
166 | HELP MODAL (EDITION-AWARE) | No 'Languages' section in sidebar | Low
167 | HELP MODAL (EDITION-AWARE) | Only Rust language card shown (no C/C++, Zig, Swift cards) | Medium
168 | HELP MODAL (EDITION-AWARE) | Books section: labeled 'The Rust Book' (specific, not 'Books') | Low
169 | HELP MODAL (EDITION-AWARE) | Books section: only Rust Book mentioned | Low
170 | HELP MODAL (EDITION-AWARE) | Security section: mentions only cargo/rustc toolchains | Low
171 | HELP MODAL (EDITION-AWARE) | Security section: 'Do not run code or binaries from untrusted sources' | Low
172 | HELP MODAL (EDITION-AWARE) | Overview lead: shows "Requires macOS 12 Monterey or later" | Medium
173 | HELP MODAL (EDITION-AWARE) | "Rust Toolchain" section appears in sidebar (between Languages and Playgrounds) | High
174 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: status table with ●/◐/○ pill explanations | Medium
175 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: "What the App Checks" lists CLT first, explains link dependency | High
176 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: two-card "Help Me Install" / "I'll Do It Myself" explanation | Medium
177 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: full manual install commands with code blocks (xcode-select, rustup curl) | High
178 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: RUSTUP_AUTO_INSTALL=0 explanation | Low
179 | HELP MODAL (EDITION-AWARE) | Rust Toolchain section: external links (rust-lang.org, rustup.rs, users forum, r/rust, etc.) all clickable | Medium
MENUS & KEYBOARD SHORTCUTS
180 | MENUS & KEYBOARD SHORTCUTS | Cmd+N — new playground | Critical
181 | MENUS & KEYBOARD SHORTCUTS | Cmd+R — run | Critical
182 | MENUS & KEYBOARD SHORTCUTS | Cmd+S — save | Critical
183 | MENUS & KEYBOARD SHORTCUTS | Cmd+, — settings | Critical
184 | MENUS & KEYBOARD SHORTCUTS | Cmd+Shift+C — copy code | High
185 | MENUS & KEYBOARD SHORTCUTS | Cmd+Shift+E — export | High
186 | MENUS & KEYBOARD SHORTCUTS | Cmd+Shift+/ — help | High
187 | MENUS & KEYBOARD SHORTCUTS | Cmd+Shift+L — toggle sidebar | High
188 | MENUS & KEYBOARD SHORTCUTS | Learn menu: only The Rust Book (Load/Remove/Read Online) | Medium
189 | MENUS & KEYBOARD SHORTCUTS | Learn menu: no K&R C Book, no Swift Book entries | Medium
190 | MENUS & KEYBOARD SHORTCUTS | Menu items grey out when no playground active | High
191 | MENUS & KEYBOARD SHORTCUTS | Menu items grey out for book projects | High
WINDOW STATE & LAYOUT
192 | WINDOW STATE & LAYOUT | Window size persists after relaunch | High
193 | WINDOW STATE & LAYOUT | Window position persists | High
194 | WINDOW STATE & LAYOUT | Sidebar width persists | High
195 | WINDOW STATE & LAYOUT | Output panel size persists | High
196 | WINDOW STATE & LAYOUT | Open tabs persist | High
197 | WINDOW STATE & LAYOUT | Active tab persists | High
198 | WINDOW STATE & LAYOUT | Resize sidebar by drag | Medium
199 | WINDOW STATE & LAYOUT | Resize output by drag | Medium
200 | WINDOW STATE & LAYOUT | Toggle sidebar: Cmd+Shift+L | Medium
201 | WINDOW STATE & LAYOUT | Layout toggle: bottom ↔ right | Medium
202 | WINDOW STATE & LAYOUT | Layout persists after relaunch | Medium
EDITION ISOLATION
203 | EDITION ISOLATION | Storage path: ~/Library/Application Support/com.rustic-playground.rust/ (NOT .app) | Critical
204 | EDITION ISOLATION | Projects created here do NOT appear in Power Edition storage | Critical
205 | EDITION ISOLATION | Config is independent from Power Edition config | Critical
206 | EDITION ISOLATION | Window state is independent from Power Edition | High
SAVED SNAPSHOT SYSTEM & REVERT
207 | SAVED SNAPSHOT SYSTEM & REVERT | Edit playground → dirty dot appears on tab | High
208 | SAVED SNAPSHOT SYSTEM & REVERT | Revert (toolbar button) → code restored to saved version | High
209 | SAVED SNAPSHOT SYSTEM & REVERT | Revert → dirty dot removed from tab | High
210 | SAVED SNAPSHOT SYSTEM & REVERT | Revert → button changes to 'Undo Revert' | High
211 | SAVED SNAPSHOT SYSTEM & REVERT | Undo Revert → dirty code restored, dirty dot returns | High
212 | SAVED SNAPSHOT SYSTEM & REVERT | Undo Revert → button changes back to 'Revert' | High
213 | SAVED SNAPSHOT SYSTEM & REVERT | Start typing after revert → Undo Revert disappears | Medium
214 | SAVED SNAPSHOT SYSTEM & REVERT | Close dirty tab → Save / Don't Save / Cancel dialog | Critical
215 | SAVED SNAPSHOT SYSTEM & REVERT | Close dirty tab → Save → file saved, tab closed | Critical
216 | SAVED SNAPSHOT SYSTEM & REVERT | Close dirty tab → Don't Save → changes discarded, tab closed | Critical
217 | SAVED SNAPSHOT SYSTEM & REVERT | Close dirty tab → Cancel → tab stays open, changes intact | Critical
218 | SAVED SNAPSHOT SYSTEM & REVERT | Edit → close without save → reopen → clean saved code (snapshot system) | High
219 | SAVED SNAPSHOT SYSTEM & REVERT | Run with unsaved changes → auto-saves before compile | Critical
RUN LIFECYCLE STATUS
220 | RUN LIFECYCLE STATUS | Run → console shows 'Saving…' info line | High
221 | RUN LIFECYCLE STATUS | Run → console shows 'Compiling…' info line after save | High
222 | RUN LIFECYCLE STATUS | Run → console shows 'Running…' info line when program starts | High
223 | RUN LIFECYCLE STATUS | All three info lines have timestamps | Low
224 | RUN LIFECYCLE STATUS | Status bar below editor shows 'Saving…' → 'Compiling…' → 'Running…' | High
225 | RUN LIFECYCLE STATUS | Build failure → status bar shows 'Build failed' | High
226 | RUN LIFECYCLE STATUS | Status bar hidden when idle (no run in progress) | Medium
STATUS BAR (VISIBILITY & LOCK ICON)
227 | STATUS BAR (VISIBILITY & LOCK ICON) | Open any playground tab → status bar visible below editor with lock icon on right | Medium
228 | STATUS BAR (VISIBILITY & LOCK ICON) | No tab open → status bar hidden | Medium
229 | STATUS BAR (VISIBILITY & LOCK ICON) | Click lock icon in status bar → toggles lock state (editor read-only / editable) | Medium
230 | STATUS BAR (VISIBILITY & LOCK ICON) | Lock icon on book project → disabled (grayed out) | Medium
231 | STATUS BAR (VISIBILITY & LOCK ICON) | Lock icon appearance when locked → highlighted in accent color | Low
READ ONLINE — BOOK CHAPTER LINK
232 | READ ONLINE — BOOK CHAPTER LINK | Select book chapter → 'Read Online' link in status bar | Medium
233 | READ ONLINE — BOOK CHAPTER LINK | Click 'Read Online' → opens correct chapter in browser | Medium
234 | READ ONLINE — BOOK CHAPTER LINK | Ch 1 → https://doc.rust-lang.org/book/ch01-00-getting-started.html | Medium
235 | READ ONLINE — BOOK CHAPTER LINK | Switch to user project → 'Read Online' disappears | Medium
236 | READ ONLINE — BOOK CHAPTER LINK | Switch between chapters → link updates correctly | Medium
TOOLBAR LAYOUT & WINDOW TITLE
237 | TOOLBAR LAYOUT & WINDOW TITLE | Toolchain pill is left-aligned (next to project switcher) | Medium
238 | TOOLBAR LAYOUT & WINDOW TITLE | Settings gear icon in toolbar-right (no border/background) | Low
239 | TOOLBAR LAYOUT & WINDOW TITLE | Settings gear opens Settings modal (⌘,) | Medium
240 | TOOLBAR LAYOUT & WINDOW TITLE | Window title: 'Rustic Rust' on launch | Medium
241 | TOOLBAR LAYOUT & WINDOW TITLE | Window title: 'Rustic Rust — project_name' when project selected | Medium
242 | TOOLBAR LAYOUT & WINDOW TITLE | Window title: 'Rustic Rust — project — playground' when tab open | Medium
243 | TOOLBAR LAYOUT & WINDOW TITLE | Window title updates when switching projects/tabs | Medium
244 | TOOLBAR LAYOUT & WINDOW TITLE | Minimum window width is 900px (can't resize smaller) | Low
245 | TOOLBAR LAYOUT & WINDOW TITLE | Toolbar controls don't overlap at minimum width | Medium
BOOK AUTO-SELECT & REACTIVE LABELS
246 | BOOK AUTO-SELECT & REACTIVE LABELS | Settings → Languages: enable language with book → book auto-checked | Medium
247 | BOOK AUTO-SELECT & REACTIVE LABELS | Settings → Languages: disable language → book hidden from Books tab | Medium
248 | BOOK AUTO-SELECT & REACTIVE LABELS | Settings → Languages: re-enable language → book still checked | Medium
249 | BOOK AUTO-SELECT & REACTIVE LABELS | Settings → Books tab: manually uncheck book → stays unchecked | Medium
250 | BOOK AUTO-SELECT & REACTIVE LABELS | Settings → Apply with language disabled → its book removed | Medium
251 | BOOK AUTO-SELECT & REACTIVE LABELS | Book/Books tab label: 1 book language = 'Book', 2+ = 'Books' | Low
252 | BOOK AUTO-SELECT & REACTIVE LABELS | Label updates live as languages toggled (no need to close/reopen) | Medium
253 | BOOK AUTO-SELECT & REACTIVE LABELS | 0 book languages → Books tab disappears, redirects to Appearance | Medium
LANGUAGE LOGOS (v0.3.3)
254 | LANGUAGE LOGOS (v0.3.3) | Open Rust playground → Rust logo (white in dark mode) as file badge | Low
255 | LANGUAGE LOGOS (v0.3.3) | Open C file (.c) → C logo as file badge | Low
256 | LANGUAGE LOGOS (v0.3.3) | Open C++ file (.cpp) → C++ logo as file badge | Low
257 | LANGUAGE LOGOS (v0.3.3) | Open Zig file → Zig logo as file badge | Low
258 | LANGUAGE LOGOS (v0.3.3) | Open Swift file → Swift logo as file badge | Low
259 | LANGUAGE LOGOS (v0.3.3) | Cargo.toml section → Cargo logo as badge | Low
260 | LANGUAGE LOGOS (v0.3.3) | Rust project selected → Cargo logo + version in toolbar | Low
261 | LANGUAGE LOGOS (v0.3.3) | C/C++ project selected → C++ logo + clang version in toolbar | Low
262 | LANGUAGE LOGOS (v0.3.3) | Zig project selected → Zig logo + version in toolbar | Low
263 | LANGUAGE LOGOS (v0.3.3) | Swift project selected → Swift logo + version in toolbar | Low
264 | LANGUAGE LOGOS (v0.3.3) | Project switcher: each project shows language logo instead of text badge | Low
265 | LANGUAGE LOGOS (v0.3.3) | Book flyout entries: language logos on book chapter items | Low
266 | LANGUAGE LOGOS (v0.3.3) | New project form (Power Edition): language logo next to project type label | Low
267 | LANGUAGE LOGOS (v0.3.3) | Toolchain Wizard: official logos on language selection cards | Low
268 | LANGUAGE LOGOS (v0.3.3) | Toolchain Wizard: language logos next to toolchain status | Low
269 | LANGUAGE LOGOS (v0.3.3) | Rust logo in dark theme → inverted to white (filter: invert) | Low
270 | LANGUAGE LOGOS (v0.3.3) | Rust logo in light theme → black (no invert filter) | Low
271 | LANGUAGE LOGOS (v0.3.3) | Other logos in dark/light → colored logos unchanged in both themes | Low
UPDATE CHECKER (v0.3.3)
272 | UPDATE CHECKER (v0.3.3) | App startup with current version → no update banner shown | Medium
273 | UPDATE CHECKER (v0.3.3) | App startup with older version (fake release) → green banner with Download + Dismiss | Medium
274 | UPDATE CHECKER (v0.3.3) | Click Download in update banner → opens GitHub release page in browser | Medium
275 | UPDATE CHECKER (v0.3.3) | Click Dismiss in update banner → banner disappears | Medium
276 | UPDATE CHECKER (v0.3.3) | Menu → Check for Updates (up to date) → toast: 'You\'re up to date' | Low

## R2 — Toolchain Wizard
Round 2: v0.3.4 Toolchain Fix Wizard — 4 Branches (Tahoe)
# | Section | Test | Priority | Pass? | Notes
BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix)
1 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Setup: vanilla VM with no Xcode CLT (xcode-select -p returns error) | Critical
2 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Pill turns red ○ (broken) on app launch | Critical
3 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Wizard toolchain step shows "○ Xcode Command Line Tools required" headline | Critical
4 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Status sub text mentions "10–15 minutes" so user knows what to expect | High
5 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Wizard detail grid shows "Xcode CLT: not found" row, hides rustup/cargo/rustc rows | High
6 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Wizard Next button is ENABLED — user can browse the app even with broken toolchain (intentional, status pill remains red) | Critical
7 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Wizard Install button labeled "Install Rust Toolchain…" opens FixWizard | High
8 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | FixWizard shows split layout: Help Me Install (guided) + I'll Do It Myself (manual) sidebar | Critical
9 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | FixWizard DEFAULTS to "I'll Do It Myself" (manual mode) — power-user-friendly default | High
10 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Manual mode: shows xcode-select --install + rustup curl command with Copy buttons | Critical
11 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Copy button changes to "Copied" briefly when clicked, then reverts | Medium
12 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Switch to "Help Me Install" → Guided mode renders with detail grid + fix actions | High
13 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Guided mode: "Install Xcode Command Line Tools" primary button visible | Critical
14 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Click guided install → triggers Apple GUI installer dialog | Critical
15 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | After click, success state shows "Apple installer launched" with prominent next-steps callout | High
16 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Callout warns dialog may be hidden behind app, suggests ⌘Tab / Mission Control | High
17 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Auto-polling: pulsing dot indicator + elapsed timer (M:SS) appears in callout | Critical
18 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Auto-polling: callout text changes from "click Re-check" to "We'll continue automatically" | High
19 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Auto-polling: status checked every 5 seconds in background | High
20 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Auto-polling stops after 30 minutes safety cap if installer hangs | Medium
21 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Auto-polling stops cleanly when modal is closed (no leaked timer) | High
22 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Switching to Manual mode mid-install is BLOCKED (sidebar buttons disabled when fixState=running) | High
23 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Apple installer completes (10-15 min) → app auto-detects via polling → cascade advances to Install Rust step (no manual Re-check needed) | Critical
24 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | After CLT install, wizard cascade progresses to next state (not_installed) and shows Install Rust action | Critical
25 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | cargo build / cargo run now works (link step succeeds) | Critical
26 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Settings → Repair Toolchain shows CLT row + Repair button when CLT absent | High
27 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | RUSTUP_AUTO_INSTALL=0 guard: check_toolchain does NOT trigger xcrun install dialog as a side effect | Critical
28 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | Toolchain panel shows "Need help with Rust toolchain?" footer with external links (rustup.rs, r/rust, etc.) | Medium
29 | BRANCH 0 — XCODE COMMAND LINE TOOLS MISSING (v0.3.4 Bug 2 fix) | External links open in default browser via shellOpen | Medium
TOOLBAR PILL — STATUS INDICATOR
30 | TOOLBAR PILL — STATUS INDICATOR | Healthy toolchain → pill shows ● (green) | Critical
31 | TOOLBAR PILL — STATUS INDICATOR | Missing rustfmt → pill shows ◐ (yellow/partial) | High
32 | TOOLBAR PILL — STATUS INDICATOR | Missing clippy → pill shows ◐ (yellow/partial) | High
33 | TOOLBAR PILL — STATUS INDICATOR | Missing both rustfmt + clippy → pill shows ◐ (yellow/partial) | High
34 | TOOLBAR PILL — STATUS INDICATOR | rustup default none → pill shows ○ (red/broken) | Critical
35 | TOOLBAR PILL — STATUS INDICATOR | rustup not installed → pill shows ○ (red/broken) | Critical
36 | TOOLBAR PILL — STATUS INDICATOR | Click pill → opens Toolchain Fix Wizard modal | Critical
37 | TOOLBAR PILL — STATUS INDICATOR | Pill color updates live after fix action completes (no manual reload) | High
38 | TOOLBAR PILL — STATUS INDICATOR | Pill tooltip shows current state description on hover | Low
FIX WIZARD — MODAL BASICS
39 | FIX WIZARD — MODAL BASICS | Wizard modal opens centered on screen | Medium
40 | FIX WIZARD — MODAL BASICS | Wizard shows cargo / rustc / rustfmt / clippy status rows | High
41 | FIX WIZARD — MODAL BASICS | Wizard shows rustup version if installed | Medium
42 | FIX WIZARD — MODAL BASICS | Wizard shows active default toolchain (stable-aarch64-apple-darwin, etc.) | Medium
43 | FIX WIZARD — MODAL BASICS | Close button (X) dismisses modal | High
44 | FIX WIZARD — MODAL BASICS | Esc key dismisses modal | Medium
45 | FIX WIZARD — MODAL BASICS | Backdrop click dismisses modal | Medium
46 | FIX WIZARD — MODAL BASICS | Wizard does NOT dismiss during an in-progress fix action | High
BRANCH 1 — HEALTHY STATE
47 | BRANCH 1 — HEALTHY STATE | Setup: rustup + default + rustfmt + clippy all installed | Critical
48 | BRANCH 1 — HEALTHY STATE | Open Fix Wizard → all status rows green | Critical
49 | BRANCH 1 — HEALTHY STATE | No "Install / Repair" fix actions shown | High
50 | BRANCH 1 — HEALTHY STATE | Wizard shows "Toolchain is healthy" confirmation | Medium
BRANCH 2A — MISSING rustfmt ONLY
51 | BRANCH 2A — MISSING rustfmt ONLY | Setup: `rustup component remove rustfmt` | Critical
52 | BRANCH 2A — MISSING rustfmt ONLY | Pill turns yellow ◐ (partial) | High
53 | BRANCH 2A — MISSING rustfmt ONLY | Open Fix Wizard → rustfmt row red/missing, others green | High
54 | BRANCH 2A — MISSING rustfmt ONLY | Single "Install rustfmt" primary button shown (no combined button) | High
55 | BRANCH 2A — MISSING rustfmt ONLY | Click Install rustfmt → output log expands inline | High
56 | BRANCH 2A — MISSING rustfmt ONLY | Output log streams rustup progress live (download/install) | High
57 | BRANCH 2A — MISSING rustfmt ONLY | After completion → silent re-check (no "Detecting toolchain" spinner) | Critical
58 | BRANCH 2A — MISSING rustfmt ONLY | Wizard refreshes to healthy state in place | Critical
59 | BRANCH 2A — MISSING rustfmt ONLY | Pill turns green ● in toolbar | High
BRANCH 2B — MISSING clippy ONLY
60 | BRANCH 2B — MISSING clippy ONLY | Setup: `rustup component remove clippy` | Critical
61 | BRANCH 2B — MISSING clippy ONLY | Pill turns yellow ◐ | High
62 | BRANCH 2B — MISSING clippy ONLY | Wizard shows single "Install clippy" primary button | High
63 | BRANCH 2B — MISSING clippy ONLY | Click → install succeeds → wizard refreshes healthy | Critical
64 | BRANCH 2B — MISSING clippy ONLY | Pill turns green | High
BRANCH 2C — MISSING BOTH rustfmt + clippy
65 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Setup: `rustup component remove rustfmt clippy` | Critical
66 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Pill turns yellow ◐ | High
67 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Wizard shows "Install rustfmt & clippy" combined primary button | Critical
68 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Individual "Install rustfmt" + "Install clippy" secondary (outline) buttons also visible | High
69 | BRANCH 2C — MISSING BOTH rustfmt + clippy | All three buttons laid out horizontally (flex-row), not stacked vertically | High
70 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Click combined button → runs sequential install | Critical
71 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Output log shows `── Installing rustfmt ──` separator | Medium
72 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Output log shows `── Installing clippy ──` separator after rustfmt finishes | Medium
73 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Both components install in unified log (no modal flash between) | High
74 | BRANCH 2C — MISSING BOTH rustfmt + clippy | After both complete → silent re-check → wizard healthy | Critical
75 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Pill turns green | High
76 | BRANCH 2C — MISSING BOTH rustfmt + clippy | Partial failure (rustfmt succeeds, clippy fails) → wizard shows clippy still missing | Medium
BRANCH 3 — NO DEFAULT TOOLCHAIN
77 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Setup: `rustup default none` (rustup installed but no default toolchain set) | Critical
78 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Pill turns red ○ (broken) | High
79 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Wizard shows "Set Default Toolchain" primary action | High
80 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Wizard shows explanatory text: "No default toolchain set" | Medium
81 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Click → runs `rustup default stable` → streams download/install | Critical
82 | BRANCH 3 — NO DEFAULT TOOLCHAIN | After completion → wizard refreshes → shows healthy or missing components | Critical
83 | BRANCH 3 — NO DEFAULT TOOLCHAIN | Pill updates to reflect new state (green or yellow) | High
84 | BRANCH 3 — NO DEFAULT TOOLCHAIN | RUSTUP_AUTO_INSTALL=0 prevents status probes from silently re-installing default | Critical
BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc)
85 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Setup: `rustup self uninstall` OR move ~/.cargo and ~/.rustup aside | Critical
86 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Pill turns red ○ (broken) | High
87 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Wizard shows "Install Rust" primary action | Critical
88 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Wizard shows explanatory text: "Rust is not installed" | Medium
89 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Click → downloads + runs rustup-init from https://sh.rustup.rs | Critical
90 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Output log streams full rustup-init output (download, install, PATH update) | Critical
91 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Network fetch works behind user firewall / captive portal (best effort) | Medium
92 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Graceful error if network fetch fails (no crash, clear message) | High
93 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | After completion → silent re-check → wizard refreshes to healthy | Critical
94 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Pill turns green ● | Critical
95 | BRANCH 4 — NOT INSTALLED (no rustup/cargo/rustc) | Subsequent `cargo run` works without app restart (PATH picked up via env) | Critical
SETTINGS → REPAIR TOOLCHAIN INTEGRATION
96 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Healthy toolchain → Settings Toolchain tab → no Repair button | Medium
97 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Broken toolchain → Settings Toolchain tab → "Repair Toolchain" button visible | Critical
98 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Click Repair → Fix Wizard opens as modal ON TOP of Settings modal | High
99 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Fix Wizard z-index (399/400) is above Settings (299/300) | High
100 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Settings modal does NOT dismiss when Fix Wizard opens | High
101 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | After fix completes → Fix Wizard closes | High
102 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Settings modal auto-refreshes in-place (no "Detecting toolchain" spinner) | Critical
103 | SETTINGS → REPAIR TOOLCHAIN INTEGRATION | Settings shows updated healthy state without user clicking Re-check | Critical
RUSTUP_AUTO_INSTALL=0 GUARD
104 | RUSTUP_AUTO_INSTALL=0 GUARD | Setup: `rustup default none` | Critical
105 | RUSTUP_AUTO_INSTALL=0 GUARD | Open app → check_toolchain command runs probes | Critical
106 | RUSTUP_AUTO_INSTALL=0 GUARD | Probes do NOT silently re-install default toolchain (guard working) | Critical
107 | RUSTUP_AUTO_INSTALL=0 GUARD | Pill correctly shows broken state | Critical
108 | RUSTUP_AUTO_INSTALL=0 GUARD | Live check during typing (check_playground) also respects RUSTUP_AUTO_INSTALL=0 | High
109 | RUSTUP_AUTO_INSTALL=0 GUARD | No background rustup network activity during idle with broken state | Medium

## R3 — Edition Upgrade
Round 3: Edition Isolation / Upgrade (Power → Rust)
# | Section | Test | Priority | Pass? | Notes
EDITION UPGRADE PATH (Power → Rust)
1 | EDITION UPGRADE PATH (Power → Rust) | Rust Edition launches without crash | Critical
2 | EDITION UPGRADE PATH (Power → Rust) | Uses separate storage (com.rustic-playground.rust, not .app) | Critical
3 | EDITION UPGRADE PATH (Power → Rust) | Wizard appears (new edition = fresh storage) | High
4 | EDITION UPGRADE PATH (Power → Rust) | No data leakage from Power Edition storage | Critical
5 | EDITION UPGRADE PATH (Power → Rust) | Existing Power Edition data unaffected after Rust Edition runs | Critical
6 | EDITION UPGRADE PATH (Power → Rust) | Both editions can run side-by-side without conflict | High
7 | EDITION UPGRADE PATH (Power → Rust) | Quitting Rust Edition does not touch Power Edition state | High

## R4 — VM Smoke
Round 4: VM Smoke Test — macOS 12 / 13 / 14 / 15 (Parallels on Mac Studio)
# | Section | Test | Priority | 12 Monterey | 13 Ventura | 14 Sonoma | 15 Sequoia | Notes
VANILLA STATE PRECHECK (run BEFORE installing DMG)
1 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | xcode-select -p → returns error (no CLT configured) | Critical
2 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | which cargo → empty (no Rust installed) | Critical
3 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | which rustup → empty (no rustup installed) | Critical
4 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | which brew → empty (no Homebrew installed) | Critical
5 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | which node → empty (no Node.js installed) | Medium
6 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | ls /Library/Developer/CommandLineTools → does not exist | Critical
7 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | ls ~/.cargo → does not exist | Critical
8 | VANILLA STATE PRECHECK (run BEFORE installing DMG) | VM snapshot name is "clean-no-dev-tools" (ready to restore after) | High
INSTALL & LAUNCH
9 | INSTALL & LAUNCH | DMG mounts without error | Critical
10 | INSTALL & LAUNCH | Drag Rustic Playground.app to /Applications | Critical
11 | INSTALL & LAUNCH | First launch: right-click → Open (unnotarized Gatekeeper path) OR normal launch | Critical
12 | INSTALL & LAUNCH | App window appears — LSMinimumSystemVersion 12.0 accepted by OS | Critical
13 | INSTALL & LAUNCH | Menu bar + Dock icon correct | Medium
14 | INSTALL & LAUNCH | No immediate crash, hang, or blank WKWebView | Critical
WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression)
15 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Welcome Wizard appears on first launch | Critical
16 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Toolchain step shows "Xcode Command Line Tools required" FIRST (before Rust state) | Critical
17 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Status sub text mentions "10–15 minutes" so user can plan | High
18 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Next button is ENABLED (user can browse the app even with broken toolchain — pill stays red as warning) | High
19 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Toolchain step shows "Need help with Rust toolchain?" footer with external links (rustup.rs, r/rust, etc.) | Medium
20 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Install Rust Toolchain button opens FixWizard modal | Critical
21 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | FixWizard shows split layout with Help Me Install + I'll Do It Myself paths | Critical
22 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Guided mode: CLT install action with prerequisite messaging | Critical
23 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Click Install Xcode CLT → Apple GUI installer dialog opens | Critical
24 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Success callout warns dialog may be hidden, suggests ⌘Tab | High
25 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Complete Apple's installer (10-15 min wait — VM may need foreground focus) | Critical
26 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Click Re-check → status transitions clt_missing → not_installed | Critical
27 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | FixWizard now shows "Install Rust" action | Critical
28 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Click Install Rust → rustup-init downloads and runs | Critical
29 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Install log streams without errors | Critical
30 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | After both installs → wizard toolchain state becomes healthy | Critical
31 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Manual mode shows Terminal commands with Copy buttons (test by switching tabs) | High
32 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Appearance step: theme preview renders | High
33 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Book step: checkbox works | Medium
34 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Finish → main UI appears | Critical
35 | WELCOME WIZARD — VANILLA FIRST RUN (Bug 2 regression) | Try ⌘R on a playground BEFORE installing toolchain → fails with clear error pointing back to toolchain modal | High
CORE RUN LOOP
36 | CORE RUN LOOP | Create new Rust project | Critical
37 | CORE RUN LOOP | Create new playground (⌘N) | Critical
38 | CORE RUN LOOP | Default Hello World compiles + runs (⌘R) | Critical
39 | CORE RUN LOOP | Output streams correctly | Critical
40 | CORE RUN LOOP | Save playground (⌘S) — no errors | High
41 | CORE RUN LOOP | Edit → revert → undo revert | High
42 | CORE RUN LOOP | Close unsaved tab → dialog appears | High
VERSION & METADATA
43 | VERSION & METADATA | Help modal (⌘⇧/) shows "Requires macOS 12 Monterey or later" | Medium
44 | VERSION & METADATA | About modal version matches 0.3.4 | High
45 | VERSION & METADATA | About modal shows "Rustic Playground — The Rust Edition" | Low
PERSISTENCE
46 | PERSISTENCE | Quit app, relaunch → window state persists (size, tabs, layout) | Medium
47 | PERSISTENCE | Project + playground still present after relaunch | Critical
48 | PERSISTENCE | No crashes, no console errors during session | Critical
CLEANUP
49 | CLEANUP | Quit app cleanly | High
50 | CLEANUP | Snapshot-restore VM to clean "no Rust" state for next run | Critical

## Issues
Issues Log
Issue ID | Title | Round | Severity | Steps to Reproduce | Expected | Actual | Notes | Fixed?